## DTT Test Hour Log
Instruction: Fill in the number of hours that were required to complete the test. Please include every step you took during the process and include a detailed description of every step. Add reasoning on why you took certain decisions or applied specific techniques. We prefer quality over quantity so take your time with the test and the log.
Subject | Amount of hours | Date | Description | Bonus
Understanding and planning the project | 0.25 | 2025-05-14 | Reading through the exercise and making an action plan, this plan details my general steps and my estimated time to accomplish them.
Preparation & Setup | 0.25 | 2025-05-14 | Configure Unity 2020.1 (or newer) and create a fresh C# project / Set up folder structure
Research & Algorithm Selection | 2 | 2025-05-14 | Review perfect maze algorithms (e.g. Recursive Backtracker, Kruskal’s, Prim’s) and choose one that balances simplicity and performance for up to 250×250 cells.
Core Maze Generation: Data model | 1 | 2025-05-19 | Define Cell class: coordinates, walls (N/E/S/W), visited. Define Maze class: width, height, 2D array of cells.
Core Maze Generation: Algorithm implementation | 3 | 2025-05-19 | Implement your chosen algorithm. Ensure no loops and full connectivity.
Core Maze Generation: Visualization | 1 | 2025-05-20 | Create a prefab or procedural mesh to draw walls/floors
UI & Configuration: UI layout | 0.5 | 2025-05-20 | Canvas with input fields for Width & Height (min10, maxs250). And “Generate” button.
UI & Configuration: Connections | 1 | 2025-05-20 | Read inputs, validate ranges, call Generate() on button click. Allow re generation at any time, cleaning up old maze.
UI & Configuration: Responsive design | 0.5 | 2025-05-20 | Test & tweak Canvas Scaler and anchors
Polish & Documentation: Code cleanup | 1 | 2025-05-20 | Consistent naming conventions, Remove duplication, adding comments ..etc
Bonus Features: Algorithm switcher | 1 | 2025-05-21 | Added a drop down to choose between backtracker and Prim’s | x
Bonus Features: Step by step generation | 1 | 2025-05-21 | Changed the code so it uses coroutine to generate and remove walls in steps for a better-looking product. | x
Bonus Features: Visual update | 3 | 2025-05-21 | Added assets and particles to make small to medium mazes look more interesting. Basic cells get used for big mazes. | x
Final Delivery | 1 | 2025-05-21 | Test the Unity project and zip entire project folder
Total amount of hours | 11.5